## Instructions
Step | What to do
1️⃣ | Open this template in your browser Make sure you’re signed into the Google account you want to own your copy.
2️⃣ | Go to File ▶ Make a copy…
- Rename it (“My Partner Scoring” or whatever you like)
- Pick a folder in your Drive
- Click OK
3️⃣ | Update your data in columns A–F; the ⚙️ helper columns (Score & Potential) will auto‑calculate.
4️⃣ | Filter or sort however you like—your formulas will carry right along!

## Planner Template
Phase | Timeline (Start – End) | Partner(s) | Key Actions | Metrics (& Targets)
30 Days | [2025-05-01] – [2025-05-30] | [ABC Company, XYZ Corp, 123 Ltd] | - Draft referral program blueprint & incentive structure- Identify top 3 potential partners- Set up unique promo code & UTM tracking | [e.g., 3 partners identified; referral link tested]
60 Days | [2025-06-01] – [2025-07-30] | [PQR Inc, LMN Group] | - Onboard first 2 partners with kickoff calls- Launch pilot co‑marketing webinar or blog swap- Collect referral data & feedback | [e.g., 2 partners onboarded; 1 webinar executed]
90 Days | [2025-08-01] – [2025-10-30] | [UVW Solutions, DEF LLC, GHI Co] | - Analyze results: referral count, close rate, revenue- Optimize incentives & outreach scripts- Scale program to top 10 partners | [e.g., 10 referrals; 40% close rate; $X revenue]

## Weekly Action Plan Template
Week | Timeline (Start – End) | Partner(s) | Key Actions | Metrics (& Targets) | Referral Count | Closed Number | Close Rate | Revenue
Week 1 | [2025-05-01] – [2025-05-07] | [ABC Company, XYZ Corp, 123 Ltd] | - Draft referral program blueprint & incentive structure- Identify top 3 potential partners- Set up unique promo code & UTM tracking | [e.g., 3 partners identified; referral link tested] | 5 | 4 | 80% | 1000
Week 2 | [2025-05-08] – [2025-05-14] | [ABC Company, XYZ Corp, 123 Ltd] | - Draft referral program blueprint & incentive structure- Identify top 3 potential partners- Set up unique promo code & UTM tracking | [e.g., 3 partners identified; referral link tested] | 8 | 2 | 25% | 1500
Week 3 | [2025-05-15] – [2025-05-21] | [ABC Company, XYZ Corp, 123 Ltd] | - Draft referral program blueprint & incentive structure- Identify top 3 potential partners- Set up unique promo code & UTM tracking | [e.g., 3 partners identified; referral link tested] | 10 | 6 | 60% | 1800
Week 4 | [2025-05-22] – [2025-05-30] | [ABC Company, XYZ Corp, 123 Ltd] | - Draft referral program blueprint & incentive structure- Identify top 3 potential partners- Set up unique promo code & UTM tracking | [e.g., 3 partners identified; referral link tested] | 12 | 7 | 58.33% | 2000
Week 5 | [2025-06-01] – [2025-06-07] | [PQR Inc, LMN Group] | - Onboard first 2 partners with kickoff calls- Launch pilot co‑marketing webinar or blog swap- Collect referral data & feedback | [e.g., 2 partners onboarded; 1 webinar executed] | 15 | 1 | 6.667% | 2500
Week 6 | [2025-06-08] – [2025-06-14] | [PQR Inc, LMN Group] | - Onboard first 2 partners with kickoff calls- Launch pilot co‑marketing webinar or blog swap- Collect referral data & feedback | [e.g., 2 partners onboarded; 1 webinar executed] | 18 | 2 | 11.11% | 3000
Week 7 | [2025-06-15] – [2025-06-21] | [PQR Inc, LMN Group] | - Onboard first 2 partners with kickoff calls- Launch pilot co‑marketing webinar or blog swap- Collect referral data & feedback | [e.g., 2 partners onboarded; 1 webinar executed] | 20 | 3 | 15% | 3500
Week 8 | [2025-06-22] – [2025-07-30] | [PQR Inc, LMN Group] | - Onboard first 2 partners with kickoff calls- Launch pilot co‑marketing webinar or blog swap- Collect referral data & feedback | [e.g., 2 partners onboarded; 1 webinar executed] | 22 | 1 | 4.545% | 4000
Week 9 | [2025-08-01] – [2025-08-07] | [UVW Solutions, DEF LLC, GHI Co] | - Analyze results: referral count, close rate, revenue- Optimize incentives & outreach scripts- Scale program to top 10 partners | [e.g., 10 referrals; 40% close rate; $X revenue] | 25 | 5 | 20% | 4500
Week 10 | [2025-08-08] – [2025-08-14] | [UVW Solutions, DEF LLC, GHI Co] | - Analyze results: referral count, close rate, revenue- Optimize incentives & outreach scripts- Scale program to top 10 partners | [e.g., 10 referrals; 40% close rate; $X revenue] | 28 | 20 | 71.43% | 5000
Week 11 | [2025-08-15] – [2025-08-21] | [UVW Solutions, DEF LLC, GHI Co] | - Analyze results: referral count, close rate, revenue- Optimize incentives & outreach scripts- Scale program to top 10 partners | [e.g., 10 referrals; 40% close rate; $X revenue] | 30 | 7 | 23.33% | 5500
Week 12 | [2025-08-22] – [2025-10-30] | [UVW Solutions, DEF LLC, GHI Co] | - Analyze results: referral count, close rate, revenue- Optimize incentives & outreach scripts- Scale program to top 10 partners | [e.g., 10 referrals; 40% close rate; $X revenue] | 35 | 8 | 22.86% | 6000

## Co-Marketing Calendar Template
Date | Activity | Owner | Audience | Notes
Week 1 | Plan joint webinar | You & Partner | Both lists | Confirm topic & format
Week 2–3 | Create content & slides | You | N/A | Co‑write slides
Week 4 | Promotion launch | Partner | Their newsletter | UTM link & promo code
Week 5 | Webinar & follow‑up | You | Registrants | Share recording

## Scorecard Instructions
Step | What to do
1️⃣ | Delete the content in colums A - F NOTE: do NOT delete G or H.
2️⃣ | Update your data in columns A–F; the ⚙️ helper columns (Score & Potential) will auto‑calculate.
3️⃣ | Filter or sort however you like—your formulas will carry right along!

## Partner Scorecard
Partner | Type | Audience Size | Engagement Score (1–5) | Referral Count | Next Touch Date | Potential | ⚙️ Helper Score ⚙️
Partner A | CPA Firm | 50000 | 5 | 6 | 2025-05-01 | Medium Potential | 6
Partner B | Bookkeeper | 300 | 1 | 1 | 2025-05-15 | High Potential | 2
Partner C | Financial Advisor | 700 | 5 | 5 | 2025-05-08 | Medium Potential | 6
Partner D | Business Coach | 600000 | 2 | 0 | 2025-05-22 | Medium Potential | 2
Partner E | Marketing Agency | 400 | 4 | 2 | 2025-05-10 | High Potential | 4
Partner F | Legal Firm | 600 | 3 | 4 | 2025-05-18 | Low Potential | 5